## IAP 24 month Roadmap CR Listing
RE-LEASE | CR # | TITLE | REQUESTOR | BRIEF DESCRIPTION | STATUS UPDATES for 01/11/2019 AB 1296 MEETING
19.2 | 109927 | Immigration Phase III | DHCS | With the implementation of CR 69974, new data elements previously unavailable in CalHEERS were made available and will be utilized to make final eligibility determinations. CalHEERS receives the citizenship verification information from the Verify Lawful Presence (VLP) interface, but cannot currently transmit the information to MEDS and/or SAWS. The implementation of this CR will also allow both a Citizen/Alien Indicator and Alien Eligibility Code to be sent to MEDS and SAWS. | CR is on track for R19.2 implementation.
R19.2 | 92298 | SSA Title II Income and Disability Indicator Verification | DHCS | This CR has two separate, primary purposes: 1) to implement electronic verification of Title II Income through the Federal Data Services hub. 2) to implement use of the SSA disability indicator to assign disabled individuals with incomes at or below 128% FPL to new aid codes L6 and L7 instead of M1 and M2. This reduces manual verifications and aligns functionality with federal funding requirements for the New Adult Group regarding populations that were Medicaid eligibility before the implementation of the ACA. | CR is on track for R19.2 implementation.
R19.2 | 126279 | Update Treatment of a Tax Dependent's MAGI-Based Income in the Individual MAGI Medi-Cal Budget | DHCS | This CR addresses a system gap to ensure MAGI based income is counted in the eligibility determination when a dependent is claimed by someone other than individuals parent and the parent is not included in the individuals MAGI household composition. | CR is on track for R19.2 implementation.
R19.2 | 92295 | FDSH VLP Interface Update to version 37 with Steps 2 and 3 | DHCS & CovCA | The California Healthcare Eligibility, Enrollment, and Retention System (CalHEERS) currently uses the H59-Verify Lawful Presence (VLP) version 33 service to verify immigration status. The Centers for Medicare & Medicaid Services (CMS) has indicated that the VLP version 33 service will be retired on April 26, 2019. It is being replaced with H104-VLP version 37 service. CalHEERS will need to upgrade from VLP version 33 to VLP version 37 as well as implement VLP steps 1a, 1b, 2 and3, making this a full version upgrade. With this upgrade, functionality will be needed so that a call to the VLP from either access channel (CalHEERS or SAWS) for all steps can be performed. | CR is on track for R19.2 implementation.
R19.2 | 123315 | 2019 R19.2 Notice Changes | CovCA & DHCS | The 19.2 notice change request will improve the NOD01 (eligibility notice) and NOD03 (45 day verification reminder notice). This change request will add a partial list of verification documents that we accept to the back of the cover page. It will also update the triggering condition for the cover page so that it will only populate when 1 or more members of the household need to send verification documents. | CR is on track for R19.2 implementation.
R19.2 | 124966 | Convert Remaining Pages to React (part 2) | CalHEERS, CovCA & DHCS | This change request will update Consumer pages to Facebook React framework. | CR is on track for R19.2 implementation.
R19.3 | N/A | Annual FPL/COLA Updates (for 2019) | DHCS | The purpose of this Annual FPL update is to implement the FPLs released by the Federal Register in January each year into CalHEERS. | CR is scheduled for R19.3 implementation.
R19.3 | 119170 | Account Transfer Phase I | CovCA | The intended outcome and output of this CR is the cross-vendor coordination between Accenture and GI to develop: 1) 1. A set of Use Case scenarios that focus on the eligibility processing interactions related to implementation of Account Transfer(AT) API for Medi-Cal, mixed household and CC (APTC or QHP only) eligible households, 2) A set of screen transition diagrams that illustrate the user experience post Account Transfer implementation for multiple scenarios for a consumers or other end users, and 3) A set of technical documents outlining the impacts. | CR is on track for R19.3 implementation.
R19.3 | 125843 | Account Transfer - GI Enrollment Notices | CovCA | This CR has two milestones. Milestone 1 will update special enrollment snippet langauge in the NOD01 to accomodate Account Transfer functionality. It will also create a new notice to inform households that add a dependent that we have auto-enrolled the new dependent in the household's current plan. Milestone 2 will include updates to NOD01 snippet language related to the blended Failure to Reconcile reasons, consent, taxes, and appeals. | CR is on track for R19.3 implementation.
R19.3 | 128196 | Data Exchange from CalHEERS to Salesforce Service Cloud | CovCA | CalHEERS is the system of record for CovCA, this CR is to get the data from CalHEERS and populate in to Sales Force software for SCR'S to have the most current information. | CR is on track for R19.3 implementation.
R19.4 | 98352 | SEP Electronic Verification Vendor Integration | CovCA | Covered California will be procuring a SEP Electronic Verification Vendor to automate the verification of SEP reasons. The anticipated SEP Electronic Verification Vendor solution will receive data from CalHEERS needed to perform SEP eligibility verification for loss of health insurance coverage. The result of the eligibility verification performed electronically by the vendor solution, with no manual intervention, will be returned to CalHEERS. CalHEERS will need to successfully integrate with the Vendor which will include updates to existing application pages to collect additional data as well as sending and receiving data between CalHEERS and the Vendor. | CR is scheduled for R19.4 implementation.
R19.4 | 123986 | Issuer Enrollment Portal Security Profile & GI Configuration | CovCA | With GI 2.0 Issuer Enrollment Portal allows the issuers access to necessary enrollment data in CalHEERS for research and analysis prior to contacting the service center. This CR is to create an Issuer Enrollment profile which is separate from the Issuer Admin profile to grant the appropriate staff access to the Issuer Enrollment Module. | CR is scheduled for R19.4 implementation.
R19.4 | 132282 | 2019 19.4 Notice Changes | CovCA & DHCS | The 19.4 notice change request will improve the NOD01 snippet langauge related to reasonable opportunity period, consolidating this information into a single section of the notice that is easy to read and understand. It will also update the NOD03 (45 day verification reminder notice) to imrpove readability and leverage the same changse made to the NOD01. Finally, this change request will update the appeals langauge to improve readability and clarity for consumers. | CR is scheduled for R19.4 implementation.
R19.4 | 119301 | BREfS Phase C - Technical Updates to separate post-eligibility business logic | DHCS & CovCA | This is a technical change request and it is part 1 of the changes. Part 2 is CR#119303. Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and eligibility business rules engine (BRE) in CalHEERS to return an eligibility determination via the Determination of Eligibility Response (DER) operation. The CalHEERS eligibility determination results must be accepted by counties, since neither the existing eHIT interface, nor the BRE functionality on the CalHEERS portal currently provide a “preview” of eligibility or the ability to override a CalHEERS eligibility determination. | CR is scheduled for R19.4 implementation.
R19.4 | 119303 | BREfS Phase C - Technical Updates to separate Eligibility and Verification processing | DHCS & CovCA | This is a technical change request and is part 2 to CR#119301. | CR is scheduled for R19.4 implementation.
R19.6 | 106890 | Income Data Quality Enhancements | DHCS | The purpose of this CR is to update the treatment of $0 income, update how certain income types are counted, update how individuals enter lump sum payments and enhance registered Domestic Partner Relationship reporting. | CR is planned for R19.6 implementation.
R19.6 | 119408 | Non-Compliance Reasons | DHCS | The purpose of this CR is for CalHEERS to provide more detail to SAWS, in the form of eligibility evaluation reasons, when a person is denied or discontinued from MAGI Medi-Cal for existing non-compliance reasons (e.g. failure to apply for Medicare). The additional detail will allow SAWS to automate NOAs and will reduce county workload. The non-compliance reasons were originally included in CR# 81756, Ineligibility Reason Codes for SAWS Notices, before being moved into the new CR# 119408. | CR is scheduled for R19.6 implementation.
2019 Q2 | 125109 | Implementation of Bounce Back Rule (CFR 435.603(i)) | DHCS | The purpose of this CR is to enhance the current Bounce Back Rule functionality. This enhancement will require individuals to meet all other APTC requirements before granting eligibility for MAGI Medi-Cal based on the Bounce Back Rule. | CR is planned for 2019 Q2 implementation.
2019 Q2 | 109744 | BREfS Phase C - Part 1: Same Day Eligibility Remediation | DHCS & CovCA | Currently, County Eligibility Workers(CEWs) processing eligibility may receive unexpected results from CalHEERS based on the incorrect case data input. In many of these occurrences the CEW’s may be able to update the case data within the same day and request for re-determination of eligibility; however, current actions require additional steps across systems and the possible use of overrides. While subsequent evaluations can remediate a consumer’s eligibility, this is not so in all cases. For instance, when eligibility of the consumer is determined outside of the expected program (i.e. MAGI Medi-Cal, APTC, etc), subsequent evaluations are ineffective when the consumer protection protocols (i.e. Soft Pause) and transition rules (i.e. Carry Forward) are factors in the same day on-going eligibility. Steps to remediate these occurrences cannot be done immediately. | CR is planned for 2019 Q2 implementation.
2019 Q2 | 126224 | 2019 19.6 Notice Changes | CovCA & DHCS | The 19.6 notice change request will consolidate and improve the 'next steps' section of the NOD01. Focus will be on improving readability and understanding of actions that the consumer must take. | CR is planned for 2019 Q2 implementation.
2019 Q2 | 125678 | Updates for Agency and Agent Portals | CovCA | The purpose of this CR is to enable the user to view Agent delegation history in CalHEERS, and perform partial Book of Business transfers with either Agencies or Agents. It will also automate various reports and notifications within CalHEERS for Agency functions. | CR is planned for 2019 Q2 implementation.
2019 | 109747 | BREfS Phase C - Part 2: Override Eligibility Determination Functionality | DHCS & CovCA | Currently, Counties have the ability to override SAWS and MEDS eligibility but CalHEERS was not programmed to consume that information and apply the updated information in CalHEERS. Under MEDIL I 14-11, DHCS provided “updated guidance on workarounds and system overrides within Statewide Automated Welfare Systems (SAWS) and the California Healthcare Eligibility, Enrollment and Retention System (CalHEERS) that are approved by the Department of Health Care Services (DHCS) for use by county eligibility workers for Medi-Cal eligibility determinations. The purpose of a workaround or override is to ensure implementation and recording of the appropriate eligibility determination when one or more automation system may not accurately implement, record, or display that information.” | CR is planned for 2019 implementation.
2019 | 82920 | BREfS Phase D - Separating Verification Service | DHCS & CovCA | Currently, the eHIT interface is a single service wherein the Eligibility Determination Request (EDR) operation engages the verification services (VIED) and eligibility business rules engine (BRE) in CalHEERS. CalHEERS uses VIED to coordinate the verifications responses into the BRE and return an eligibility determination via the Determination of Eligibility Response (DER) operation. | CR is planned for 2019 implementation.
2019 | 61104 | Plan Dependency Definition | CovCA | The CalHEERS System shall allow multiple primary tax filers with multiple APTC eligibility/amounts on the same case/application. The CalHEERS system shall only allow the following individuals to enroll in the same Covered CA enrollment group/plan: Married spouses; Registered domestic partners; Biological/adopted/step/certified child under age of 26, including those of Registered Domestic Partners; Disabled adult children of any age (including 26 or above); Siblings under the age of 19. | CR is planned for 2019 implementation.
2019 Q3 | 122183 | Medi-Cal Deemed Infant and Medi-Cal Access Infant Program Functionality | DHCS | The purpose of this CR is to: 1) Program functionality into CalHEERS for the Deemed Eligibility for Infants program, including SAWS requirements. To allow Deemed Infants to be added to the case of a MAGI Medi-Cal mother while bypassing all tax household information. 2) Provide full functionality to register infants in CalHEERS for the Medi-Cal Access Infant Program (MCAIP) allowing infant(s) (E6/E7) to be added to the case of a Medi-Cal Access Program (MCAP) mother while requiring a MAGI determination at infant registration. 3) Add MCAIP E6/E7 infants eligibility and renewal functinality to CalHEERS. | CR is planned for 2019 Q3 implementation.
2020 | 82978 | County Inmate Program | DHCS | The purpose of this CR is to allow CalHEERS to accept applications for County MCIEP from the SAWS access channel. County staff will be able to process eligibility for County Inmate Program (Aid Code N7 and N8) and County Compassionate Release/Medical Probation Program (Aid Code K6, K7, K8, and K9). | CR is planned for 2020 implementation.
2020 | 95185 | SEP Pre-Enrollment Verification | CovCA | Add verification to verify SEP Reasons before consumers are effectuated in a QHP/QDP. | CR is planned for 2020 implementation.
2020 | 95184 | SEP Dropdown and Workflow | CovCA | The intended outcome is: 1. Update and add to the available SEP reasons, 2. Update and add to the business rules for each existing and new SEP reason and coverage date category, 3. Dynamically display the SEP reasons in the dropdown list based on the user role and application mode, and 4. Update eHIT/SAWS accordingly | CR is planned for 2020 implementation.

## Status Def
Status | Definition
Accenture Access Impact | Once CCB approves the CR to move from "Proposed" to "Accenture Assess Impact", Accenture will analyze based on business requirements and identify initial Rough Order of Magnatitude (ROM) cost. In parallel track, the State also conducts its analysis (see State Assess Impact). Once CCB reviews and approves the requirements and cost estimation, the CR status becomes "Approved for Design".
Approved for Design | Once CCB approves for Design, the CR status becomes "Approved for Design". This authorizes Joint Application Design (JAD) sessions to begin where requirements are reviewed and designs of the system functionalities are documented. The output from the JADs is the final design document for the CR.
Approved for Implementation | Once the design artifacts are signed off by the sponsor(s), the CalHEERS State staff will verified and updated cost information and present to CCB for final approval. Once CCB approves, the CR status becomes "Approved for Implementation".
CCB Review | The Change Control Board (CCB) consists of three voting members; they are the Project Director of CalHEERS, the Chief Tecnology Officer of Covered CA, ad the Chief Information Officer of Department of Health Care Services). As CRs enter each phase of the Software Development Life Cycle (up to Build), they are presented to the voting members for review and approval. When a CR are presented to the Change Control Board (CCB) for approval, any actions items related to the CR are captured and mitigated prior to CCB determining approval/non-approval.
Closed | All work completed, verified, and invoiced.
Mitigated | This status identifies items that are reported as ‘in the system’; however, there were no requirements or artifacts that reference the solution. As such, until the State receives documentation and the resolution is reviewed and approved, the changes remain in "Mitigation" status.
New | After following internal governance process, the sponsor (DHCS or Covered CA) or CalHEERS initates the Change Request (CR). The CR is created and recorded in the CalHEERS Project's change request tracking system. The CR status becomes "New".
Proposed | After creating and recording the CR, additional details are added to the CR by the CalHEERS business analyst(s), and an email is sent to the CalHEERS' State Change Control Lead. The CR status is changed to "Proposed" where the next step is for the Change Control Board to review and approve.
State Access Impact | Once CCB approves the CR to move from "Proposed" to "State Assess Impact", the State will analyze impact and determine readability. In parallel track, Accenture also conducts their analysis (see Accenture Assess Impact). Once CCB reviews and approves the requirements and cost estimation from Accenture, the CR status becomes "Approved for Design".

## Acronyms
Acronym | Definition
ACA | Affordable Care Act
ACWDL | All County Welfare Directors' Letter
AE | Accelerated Enrollment
AIM | Access for Infants and Mothers (now know as Medi-Cal Access Program)
APTC | Advanced Premium Tax Credit
AR | Authorized Representative
ASHS | Applicable State Health Subsidy
BDA | Beginning Date of Aid
BI | Business Intelligence
BPEL | Business Process Execution Language
BRE | Business Rules Engine
BSD | Business Service Definition
CalHEERS | California Healthcare Eligibility, Enrollment, and Retention System
CalHSMI | CalHEERS / SAWS / MEDS Interface
CalWIN | One of the three SAWS, provides service to 18 counties
CalWORKS | California Work Opportunities and Responsibility for Kids
CCHIP | California Children's Health Insurance Programs
CDSS | California Department of Social Services
CE | Continuous Eligibility
CEC | Continuous Eligibility for Children
CEE | Certified Enrollment Entity
CEW | Certified Eligibiilty Worker
CFR | Code of Federal Regulations
CIA | Certified Insurance Agent
CIN | Client Index Number
C-IV | One of the three SAWS, provides service to 39 counties
CMS | Centers for Medicare & Medicaid Services
CPP | Consumer Protection Programs
CSR | Cost Sharing Reduction
CWDA | (CA) County Welfare Directors Association
DE | Deemed Eligibility
DER | Determination Eligibility Response
DHCS | Department of Health Care Services
DMV | Department of Motor Vehicles
DSH | (Federal) Data Services Hub
ECM | Enterprise Content Management
EDR | Eligibility Determination Request
eHIT | Electronic Health Information Transfer
eICT | Electronic Inter-County Transfer Interface
ESB | Enterprise Service Bus
EW | Eligibility Worker
FFC | Former Foster Care
FFM | Federally Facilitated Marketplace
FPL | Federal Proverty Level
GI | General Inquiry
HCO | Health Care Options
HTTP | HyperText Transfer Protocol
HTTPs | HyperText Transfer Protocol Secure
HX | Health Exchange and Medi-Cal Interface (HEMI) Transaction
IAP | Insurance Affordability Program
ICD | Interface Control Document
ICT | Inter County Transfer
IDD | Interface Design Document
IFSV | Income and Family Size Verification
INS | Immigration and Naturalization Service
IRS | Internal Revenue Service
JAD | Joint Application Design
LEADER | One of the three SAWS, provides service to Los Angeles county
LP | Lawful Presence
LRS | Leader Replacement System
M/C | Medi-Cal
MAGI | Modified Adjusted Gross Income
MEC | Minimum Essential Coverage
MEDS | Medi-Cal Eligibility Data System
MOE | Maintenance Of Effort
NA Back 9 | A universal back page to be used on all NOAs for Medi-Cal, CalWORKS, and/or CalFresh.
NOA | Notice of Action
NOD | Notice of Deficiency | Notice of Decision?
NQI | Newly Qualified Immigrants
OBIEE | Oracle Business Intelligence Enterprise Edition
OPA | Oracle Policy Administration
OTech | Office of Technology Services (under California Department of Technology)
PA | Public Assistance
PAI | Projected Annual Income
PBE | Plan-Based Enroller
PII | Personally Identifiable Information
PMPM | Per Member Per Month
PRUCOL | Permanently Residing Under Color of Law
QHP | Qualified Health Plan
QNC | Qualified Non-Citizen
RIDP | Remote Identify Proofing
RRV | Renewal and Redetermination Verification
SAWS | Statewide Automated Welfare System
SBM | State-Based Marketplace
SCR | Service Center Representative
SFTP | Secure File Transfer Protocol
SLA | Service Level Agreement
SOAP | Simple Object Access Protocol
SOC | Share of Cost
SSA | Single Statewide Application
SSI/SSP | Supplemental Security Income/State Supplementary Payment
SSL | Secure Sockets Layer
SSN | Social Security Number
TBD | To Be Determined
TMC | Transition Medi-Cal
UAT | User Acceptance Testing
UI | User Interface
VLP | Very Lawful Presence
XML | Extensible Markup Language