## Go-Live Dates
Acronyms are defined on the Acronyms sheet. Use Control + page down to navigate to the new sheet. Bold Cells indicate changes from prior version. | DHCS Major Program Initiatives - Go-Live Dates (pending readiness and federal approvals) | [15 empty] | Updated: 2/1/2023
Category | Activity | 7/22 | 10/22 | 12/22 | 1/23 | 2/23 | 3/23 | 4/23 | 6/23 | 7/23 | 10/23 | 1/24 | 4/24 | 5/24 | 7/24 | 12/24 | 1/25 | 7/25 | 12/25 | 1/26 | 2027
CalAIM/Waiver | Administrative Integration of SMH and SUD |  |  |  | Phase I Voluntary Integration of Behavioral Health Functions | [12 empty] | Phase II Voluntary Behavioral Health Contract Integration (County Option) |  |  | Fully Integrated
| Benefits Standardization |  |  |  | Skilled Nursing Facility Carved Into Managed Care |  |  |  |  | Specialty Mental Health Carved Out of Managed Care1 |  | ICF/DD & Subacute Care Facilities Carved Into Managed Care
| Enhanced Care Management (ECM)/Community Supports (ILOS) | X |  |  | X |  |  |  |  | X |  | X
| Incentive Payment Program |  |  |  | X | [6 empty] | X
| Mandatory Managed Care Enrollment |  |  |  | Duals
| PATH Initiatives (ECM, Community Supports, Justice-Involved) |  |  | CITED Round 1 WPC Services & Collaborative Planning | TA Marketplace (Jan 23) CITED Round 2 Opens (Q1 2023) |  |  |  |  | CITED Round 3 Opens (Q3 2023) |  | CITED Round 4 Opens (Q1 2024)
| Regional Capitation Rates and Shared Savings/Risk |  |  |  | SPD & LTC Blend In COHS | [6 empty] | SPD & LTC Blend Non-COHS2 Retrospective Shared Savings2 |  |  |  |  | X |  |  | X | Prospective Shared Savings
| Behavioral Health No Wrong Door | X
| Contingency Management |  |  |  | Q1 2023
| SMI/SED IMD Waiver (CalBH-CBC Waiver) | [8 empty] | Earliest to CMS |  | X
| Transition to Statewide LTSS and D-SNP (CCI ends) | Feasibility Study |  |  | CCI Counties | [14 empty] | Non-CCI Counties | Statewide MLTSS
| Behavioral Health CPT Code Transition | [8 empty] | X
| Behavioral Health Standard Screening and Transition Tools |  |  |  | X
| Justice-Involved Initiative |  |  |  | Pre-Release Medi-Cal Application | [7 empty] | Pre-Release Medi-Cal Services (24-month phase-in period begins)
| Population Health Management (including Service (TBD)) |  |  |  | PHM Program
| Behavioral Health Payment Reform | [8 empty] | X
| County CCS Oversight | [13 empty] | X
| NCQA Accreditation | [18 empty] | X
| Full Integration Plans | [19 empty] | X
| County Eligibility and Oversight | [12 empty] | X
DMC-ODS Traditional Healers and Natural Helpers (TBD)
Improving Beneficiary Contact and Demographic Information (TBD)
Children and Youth Behavioral Health (BH) Initiative | School-Linked Partnership/Capacity/Infrastructure Grants | [7 empty] | X
| Evidence Based and Community-Defined Evidence Practices Grants |  |  | X
| Provider Education Campaign | [7 empty] | X
| BH Service Virtual Platform (including e-Consult) | [10 empty] | X
| Statewide All-Payer Fee Schedule and BH Network | [10 empty] | No Sooner Than
Behavioral Health Continuum Infrastructure Program (BHCIP) | Release Round Five RFAs: Crisis and Behavioral Health Continuum |  | X
| Release Round Six RFAs: Outstanding Needs Remaining After Rounds 3 Through 5 | [13 empty] | No Sooner Than
Home and Community Based Services (HCBS) Spending Plan | Non-IHSS HCBS Care Economy Payments | [6 empty] | Q2 2023
| LTSS Data Transparency | X
Eligibility | Eliminate Medi-Cal Asset Test | X | [9 empty] | X
| Expansion of Full-Scope Medi-Cal Coverage to All Adults Regardless of Immigration Status | [10 empty] | X
Benefits | Behavioral Health Peers | X
| Community Health Worker | X
| Doula |  |  |  | X
| Dyadic Services |  |  |  | X
| Medi-Cal Rx |  |  |  | Phase II |  | Phase III (3-month Phase) |  |  | Phase IV
| Mobile Crisis Services |  |  |  | X
| Continuous Coverage for Age 0-5 | [15 empty] | X3
| Share of Cost Reform | [15 empty] | X3
Financial | FQHC Alternative Payment Methodology | [10 empty] | X
| Skilled Nursing Facility - Quality Assurance Fee Reform |  |  |  | X
| Equity and Practice Transformation Payments |  |  |  | Planning Application Released (Q1 2023) |  |  |  |  | Application Released (Q3 2023) |  | Cohort I Directed Payment Program Begins (Q1 2024) |  |  |  |  | Cohort II Directed Payment Program Begins (Q1 2025)
| Retention Payments to Qualifying Health Facility Workers |  |  |  |  | Hospital / Skilled Nursing Facility | Clinic
Other | Drug Medi-Cal Parity Investments |  |  |  | X
| Medi-Cal Managed Care New Contract | [10 empty] | X
| Behavioral Health Bridge Housing Program |  |  |  |  | RFA Released | Conditional Awards (March - May)
| Community Assistance, Recovery and Empowerment (CARE) Court | [9 empty] | Cohort I |  |  |  |  | Cohort II |  |  | Full Implementation
Health Equity Roadmap (TBD)
Bold cells indicate change from prior version
Quarters (Q) are based on calendar quarter
1 Solano and Sacramento Counties only
2 Potential phase in through 2026, as applicable
3 Subject to appropriation, federal approval and state readiness

## Acronyms
Acronyms | Definition
BH | Behavioral Health
CalAIM | California Advancing and Innovating Medi-Cal
CalBH-CBC | ​​​​​​California Behavioral Health Community-Based Continuum
CCI | Coordinated Care Initiative
CCS | California Children's Services
CITED | Capacity and Infrastructure Transition, Expansion and Development
CMS | Centers for Medicare & Medicaid Services
COHS | County Organized Health Systems
CPT | Current Procedural Terminology
DMC-ODS | Drug Medi-Cal Organized Delivery System
D-SNP | Dual Eligible Special Needs Plan
ECM | Enhanced Care Management
FQHC | Federally Qualified Health Center
HCBS | Home and Community Based Services
ICF/DD | Intermediate Care Facility for the Developmentally Disabled
IHSS | In-Home Supportive Services
ILOS | In Lieu of Services (renamed Community Supports)
IMD | Institution for Mental Diseases
LTC | Long Term Care
LTSS | Long-Term Services and Supports
MLTSS | Managed Long-Term Services and Supports
NCQA | National Committee for Quality Assurance Accreditation Workgroup
PATH | Providing Access and Transforming Health
PHM | Population Health Management
RFA | Request for Application
SED | Serious Emotional Disturbance
SMH | Specialty Mental Health
SMI | Serious Mental Illness
SPD | Seniors and Persons with Disabilities
SUD | Substance Use Disorder
TA | Technical Assistance
TBD | To Be Determined
WPC | Whole Person Care