## Open Items
Item Number | Date Logged | Policy Topic | Requestor | Action Item | Responding Organzation | Owner | Deadline | Status | Notes
1 | 2016-09-07 | Renewal Language | Stakeholder | Covered CA to provide final notices with renewal languages based on CR# 59948. | Covered CA | Valerie York |  | Completed & Closed | Action item closed at the 1/13/17 meeting.
2 | 2016-09-07 | SAWS | Stakeholder | CWDA to check with SAWS to determine if the SAWS have the functionality to provide text messages and/or automatic phone calls. | CWDA | Assmaa Elayyat |  | Completed & Closed | 5/31/17 - CWDA/Cathy provided the response at the meeting.
3 | 2016-09-07 | Report a Change | Stakeholder | In a meeting with CWDA, the advocates understood from counties that for report a change of income, whole family will be re-evaluated. How will this impact those on APTC? | Covered CA | Thien Lam |  | Completed & Closed | 9/7/16 - Thien will circle back with Cori R. to clarify and respond. 1/13/17 - CC/Thien provided responses to question at the meeting.
4 | 2017-01-13 | n/a | Stakeholder | In addition to .pdf versions for the agenda and the CR Update document, post the Microsoft version. It will enable stakeholders to make necessary notes. | DHCS | Fei Collier/ Doina Culiuc |  | Completed & Closed | 8/24/17 - Update -- Due DHCS website publication standards, the Microsoft version of the documents will be posted on the AB 1296 website whereever possible instead of the including the .pdf version. 5/31/17 - Microsoft version and the .pdf version, for the Agenda and the CR Update document, have been posted on the AB 1296 website for the 5/31/17 meeting.
5 | 2017-01-13 | n/a | Stakeholder | For future IV&V Summaries, DHCS, Covered CA, and CalHEERS will discuss the strategy on how to build upon the IV&V reporting calendar and complete a roll up view for future IV&V updates. | CalHEERS / DHCS / Covered CA | CalHEERS / DHCS / Covered CA |  | Open | 8/24/17 - CalHEERS, DHCS, and Covered CA will continue to explore the opportunitis in future meetings to share the IV&V reports. 5/31/17 - CalHEERS, DHCS, and Covered CA will discuss the strategy in a future date.
6 | 2018-01-12 | n/a | CH Project | All stakeholders to provide final comments to the 2019 Initiatives list by COB 1/19/18. | Stakeholders | CalHEERS / DHCS / Covered CA | 2018-01-19 | Closed
7 | 2018-01-12 | Horizontal Integration | Stakeholder | Stakeholder requested DHCS could consider horizontal integration as a future initiative | DHCS | DHCS |  | Open
8 | 2018-01-12 | State Inmate | Stakeholder | Stakeholder requested further discussion and understand of the State Inmate CR (#82977). DHCS will add to the next CFSW or schedule separate meeting. | DHCS | DHCS |  | Open