## Legend
Legend
Log Items | Description
Item Number | 1, 2, 3…Numerically list the action item number.
Date Logged | Date that the action item was logged.
Category | Insert the policy topic of action item. Please see below for list of MCED approved topics.
Action Item | Description of action item.
Owner | List owner.
Deadline | Deadline when action item needs to be completed.
Status | See below for status options.
Notes | Put in updates or additional notes related to this action item.
Category | Status
Open
Closed
Not yet started

## Open Items
Item Number | Date Logged | Policy Topic | Division or Branch | Action Item | Requestor | Owner | Deadline | Status | Notes
1 | 2014-10-15 | Policy Status | MCED | Monthly ACWDL/MEDIL status reports |  | Crystal |  | Closed | Sent 10/16.
4 | 2014-10-15 | Data | Program Review | Renewal data request: updated numbers of terminations, response rate, breakdown by counties. What kind of reporting data can advocates expect to see? |  | Braden |  | Closed | Will discuss in CFSW meeting as the same action item is open there.
1 |  | Data | MCED, Policy Dev. | Advocates asked for renewal data broken down by county. |  | Rocky |  | Open | Renewal data will be in ABx1_1 report.
2 |  | Data | MCED, Policy Dev. | Advocates asked for renewal data on: a. County by county discontinuances; top 15-20 counties. b. Discontinuances by applicants’ primary language, re: failure to reply. c. Those who are reinstated during cure period. |  | Clarissa |  | Open | In progress.
7 | 2014-10-15 | IT | ITSD | ITSD briefing on MEDS Modernization |  | Crystal |  | Closed | Will discuss in a November CFSW meeting.
3 |  | FFY, Data | MCED, Policy Op | Issue 2 ACWDLs to clarify former foster youth enrollment into Medi-Cal. |  | Ernesto |  | Open | 1st ACWDL to address Groups 1+2. 2nd ACWDL to address Group 3.
9 | 2014-10-15 | SOC | Policy Ops | a. Under review. |  | Sharyl |  | Closed | Instructions covered in Pub 68, "Medi-Cal What it Means to You."
11 | 2014-10-15 | Income | Policy Ops | a. CWDA working with SAWS to implement language. |  | Harold |  | Closed | Sent 10/24.
4 | 2015-01-09 | HPE | MCED | Update HPE portal to eliminate denials for APTC eligibility. | Legal Aid of San Diego & NHELP & WCLP | Ernesto |  | Closed | The “Hospital PE Clarification Regarding Applicant Eligibility” article is now available in the NewsFlash area and the ACA Hospital Presumptive Eligibility (PE) Program page of the Medi-Cal website. Shared copy of final bulletin with advocates.
5 | 2015-02-20 | Pregnancy | MCED | NEW: Develop pregnancy fact sheet and publish. PREVIOUS: Go back and confirm pregnancy language on SSApp (Oct. 2014 version). |  | Ernesto |  | Open | Advocates reviewed. OPA to coordinate publishing with Covered CA.
6 | 2015-03-06 | Lump Sum | MCED | Kim will send 3 or 4 lump sum scenarios to test in CalHEERS. | Kim Lewis | Kim Lewis |  | Open | Kim is lead now, replacing Sonal.
7 | 2015-03-18 | Immigration | MCED | Can DHCS issue the Trafficking and Crime Victims Assistance Program ACWDL on SB1569 that has been in the works since 2006-07? | Jen Flory | Harold/John |  | Open | TCVAP ACWDL being drafted. CWDA provided input. Will be released for review by 6/12.
8 | 2015-05-01 | FPL, Outreach | MCED | Advocates would like to review the outreach letter for FPL changes, re: Medi-Cal aid codes. |  | Carol |  | Open | 2nd Review sent 6/8.
9 | 2015-05-01 |  | CWDA | Assmaa will confirm MC-216 programming changes in SAWS. |  | Assmaa |  | Open | C-IV schedule for later this summer. No updates from Cal-WIN or LEADER.
10 | 2015-05-13 |  | MCED | Can DHCS provide a list of notices from counties and CalHEERS, re: MC to CC? |  | Clarissa |  | Open | ACWDL in development. CWDA provided comments.
11 | 2015-05-29 |  | MCED | DHCS to review cases where individuals moved from full-scope to restricted-scope for no apparent reason. |  | John |  | Open | Researching with CWDA and CalHEERS.
12 | 2015-05-29 |  | CWDA | Look into how many people are coming into Medi-Cal from SAWS 2+ and CalFRESH applications. |  | Assmaa |  | Open
13 | 2015-05-29 | Data | MCED | Provide overview of ABx1_1 Report at CFSW meeting. |  | Rocky |  | Open | To be held in June 12.
14 | 2015-06-05 | SOC | MCED | Provide breakdown of those on SOC by health coverage: under 65, under 65 Medicare A or B, Dual APTC, under 65 with OHC, and under 65 w/o OHC. |  |  |  | Open
15 | 2015-06-05 | Waiver | MCED | Advocates would like to discuss how to perform outreach on parents of children with Medi-Cal. |  | CWDA/ Clarissa |  | Open | To be held in June 12.
16 | 2015-06-05 | FPL | MCED | Provide clarification on different FPL levels listed for Medi-Cal programs. Advocates would like to understand why there are discrepancies or if one list supercedes another. |  |  |  | Open

## Ongoing Items
Item Number | Date Logged | Policy Topic | Division or Branch | Action Item | Requestor | Owner | Deadline | Status | Notes
1 |  | Federal Reporting | HCBE/ MCED | Provide screenshots of SOCRATA (what was provided to CMS). |  | Rocky |  | Open | Monthly Ongoing. Last one sent on 5/1.
2 |  | APTC to MC, MC to APTC | MCED/CC | DHCS and Covered California will share updates on transition issues as they develop. Specifically: system changes, policy changes, soft pause. |  |  |  | Open | Ongoing
3 | 2015-04-13 |  | MCED | Can DHCS-MCED provide a comprehensive list of ACWDLs in development? |  | Alice/ Crystal |  | Open | Quarterly ongoing. Shared 5/13.

## Closed Items
Item Number | Date Logged | Policy Topic | Division or Branch | Action Item | Requestor | Owner | Deadline | Status | Notes
1 | 2015-01-23 | Medi-Cal Transition | MCED | Coordinate with CC on transition issues and appeals process. Have a meeting between CC, DHCS and advocates. | Jen Flory | Matt |  | Closed | DHCS, CC, CWDA and advocotes met on 2/18.
2 |  | NOA | MCED, Policy Op. | DHCS will confirm 90 Day Cure Period NOA snippets is implemented. |  | Kennalee/ Alison |  | Closed | Completed
3 | 2015-01-09 | Eligibility Systems | MCED | Can CalHEERS and MEDS identify someone who is eligible for Covered California, but not enrolled? | Sonal Ambegaokar | Ernesto |  | Closed | MCED to assess level of effort/cost of programming across systems to address concerns raised.
4 | 2015-01-09 | eHIT | MCED | eHIT interface issues between CalWIN and CalHEERS. Maria to receive specific scenarios. | Trinh Pham, Legal Aide Society of San Mateo | Harold/ Maria |  | Closed | It may be that the transaction was not ‘read’ correctly. If the income is not entered correctly in SAWS so that CalHEERS can read it correctly, the eligibility determination will be incorrect.
5 | 2014-11-14 |  | MCED | Retro Medi-Cal in CalHEERS |  | Maria/ Yingjia |  | Closed | Harold, Maria and Yinjia can provide review of policy.
6 | 2014-11-21 |  | HCBE/ MCED | Concern about volume of ACWDL’s and MEDIL’s, and complexity/changing instructions to counties. Katie Murphy suggested that we ask foundation for help to develop simplified, consolidated guidance for counties. |  | Rene/Tara |  | Closed | Recommendations made to Rene.
7 | 2014-11-21 |  | MCED, Policy Dev. | Concerns around NOAs. Questions about why the changes from last year are still not implemented. Suggestion that CC develop workarounds for NOAs that won’t be fixed for a while. Language issues, alternate format notification issues. |  | Clarissa | 2014-12-01 | Closed | Recommendations made to Rene.
8 | 2014-11-21 | O&E | MCED, Policy Op. | Interested in more outreach around enrollment for prisoner re-entry, especially in light of ballot initiative and new wave of re-entry. |  | Crystal | 2014-12-01 | Closed | Crystal and OE team met with Safe and Just on 12/8.
9 | 2014-11-21 |  | Assoc. Director | AB 1296: want a deeper dive, or special subgroup, to better understand timeline and prioritization process for system changes and improvements. |  | Anastasia |  | Closed | Automation Systems Coordination and Prioritization Subgroup met on 12/19.
13 | 2015-02-20 |  | MCED | Send comment log and .pdf of paper app. |  | Matt |  |  | Posted online on 2/24.
8 | 2015-02-06 | HPE, FFY | MCED | Review HPE guidance and policy. Is there anyway for FFY to utilize HPE application as it is shorter? |  | Ernesto |  | Closed | Draft guidance sent to HPE workgroup. In production: quick news flash and provider bulletin.
9 | 2015-02-20 |  | MCED | Share draft guidance, re: Action Item 8. |  | Ernesto |  | Closed | Draft shared.
10 |  | FFY, Data | MCED, Policy Op | Advocates are looking for #'s on former foster youth. Is there any outreach being done for those in APTC? Need to discuss refunding premiums for those effecuated a QHP. Need to provide retro-coverage to date of original application. |  | Ernesto |  | Closed | Working with counties and convening with Covered California. Data release approved by Privacy Office.
11 | 2015-02-06 | HPE, FFY | MCED | Review HPE guidance and policy. Is there anyway for FFY to utilize HPE application as it is shorter? |  | Ernesto |  | Closed | Draft guidance sent to HPE workgroup.
12 | 2015-02-20 | FFY | MCED | Go back and confirm FFY language on Slide 6 of SSApp (Oct. 2014 version). |  | Ernesto |  | Closed | Language was changed, update was provided on 3/6.
3 | 2014-11-14 |  | MCED, Policy Dev. | Issue ACWDL to clarify address changes via Managed Care Plans |  | Clarissa/ Carol |  | Closed | Released 4/16.
10 | 2015-03-20 |  | MCED/ CC | Can DHCS and CC establish points of contact for advocate referrals? |  | Robert/ Thien |  | Closed | Donna Brass and Rose Pankratz are the DHCS contacts. Sent out 3/20.
12 | 2015-03-20 |  | MCOD | What is the legal authority for how DHCS can move people into a plan without providing their choice option? |  | Javier |  | Closed | Javier provided update at 4/17 meeting.
13 |  |  | MCED | DHCS will share any trends resulting from the county site visits. |  | Alice |  | Closed | Sent out 5/1.
4 | 2015-02-06 | SOC | MCED | Data run of how many people are in medically needy SOC aid code as of January 2015 (or most current). Compare January 2014 to January 2015. | Jen Flory | Clarissa |  | Closed | Shared at 5/1 meeting.
9 | 2015-03-20 |  | CC | Covered California will confirm protocols and share further guidance on transition issues. APTC to Medi-Cal, Medi-Cal to APTC. |  | Thien |  | Closed | Provided Medi-Cal to APTC, APTC to Medi-Cal, and batch workaround process flows.
11 | 2015-04-17 | RFTHI | MCED | What RFTHI form is being sent out by the counties? |  | Clarissa |  | Closed | Counties are sending out 2014 RFTHI. Updates to 2015 RFTHI in process but need Advocates’ comments to confirm all comments are incorporated into current draft. Next steps, we will align the draft 2015 RFTHI with new SSA on income and household composition.
12 | 2015-04-17 | MC 216 | MCED | Are the translated MC 216s programmed into CalHEERS and SAWS? |  | Clarissa |  | Closed | The MC216 has been translated in all threshold languages. Per ACWDL 15-09, issued 1/30/15 the SAWS are to program their systems accordingly. Per CWDA on 4/17/15, the SAWS consortia are working on this but has not completed the programming.
15 | 2015-05-01 |  | MCED/CC | Anjie to connect with Robert on points of contact. |  |  |  | Closed | Anjie will provide update at 5/15 meeting.
16 | 2015-03-06 | Immigration | MCED | NEW: John to connect with Sonal on starting Immigration workgroup. PREVIOUS: John to connect with Sonal on PRUCOL issues regarding the 15.3 release. | Sonal | Harold/John |  | Closed | First meeting June 1st. Scheduled eery other week.
17 | 2015-05-01 | Outreach | MCED | Advocates would like to review draft of outreach letter for beneficiaries on non-MEC Medi-Cal programs. |  | Carol |  | Closed | ACWDL- 14-33.
18 | 2015-05-01 |  | MCED | What is the SOC policy at the county level? |  | Assmaa |  | Closed | Discussed at 5/15 meeting.