## Open Action Items
Item Number | Date Logged | Action Item | Owner | Status | Notes
1 | 2015-06-15 | How many people are waiting to complete an application due to RIDP. What are the numbers today? | Covered CA | In Progress | As of July 2015 there were 42,237 individuals who started an application and did not complete it. Covered CA to follow up on what happened to these applicants (how many applicants completed the application etc.). RIDP screenshots sent out to the group. 03/21/16 - No update. Bianca to send clearer RIDP screenshots. 04/18/16 - No update.
2 | 2015-07-13 | Share process of manual verification to ensure there are not repeat requests for immigration status. Confirm that we are not asking consumers for information again because the information is not being retrained with their case. | Covered CA | In Progress | Advocates want an analysis of anyone who is not newly eligible. Covered CA will follow up on their request. Covered CA states that this information can not be split by race/ethnicity etc. Previous question: Are the 80,000 inconsistencies related to immigration or citizenship status for newly eligibles? Clarify if these are new cases. Can this information be spilt by race/ethnicity/language? 03/21/16 - No update. 04/18/16 - No update.
3 | 2015-10-02 | Individuals in a status (such as student visas) – who are not eligible for full-scope Medi-Cal due to their immigration status, but are lawfully present for Covered CA purposes should get APTC even though their income is below 138% of the FPL. Is there a task guide to address this until it is fixed? | Covered CA | In Progress | Covered CA to elevate this issue to see what work arounds are available. Advocates to provide cases to Covered CA to look at. Additional information sent by Cori. Reviewing CR 32277 to see if this CR will help this issue. If not Covered CA will open a new CR to address the issue. Advocates would like to know what work around can be used. What would the outcome of a hearing be? 03/21/16 - No update. 04/18/16 - No update.
4 | 2015-11-02 | Review SSN recommendations provided by Advocates. | MCED | In Progress | Draft language shared with advocates. Feedback was received and shared back with advocates. There is a placeholder in an upcoming CR to make text edits.
5 | 2015-12-24 | Deferred Action for Parents of Americans (DAPA), where is this in the process and is this something we are preparing for coming soon. | MCED | In Progress | The Supreme Court has heard the oral arguments on the DAPA litigation. No further updates.
6 | 2016-03-07 | Can information regarding expedited enrollment be added to SB 75 letter #3? | MCOD | In Progress | The letter contains information about how to enroll in Managed Care. An individual does not need to wait for enrollment packet. An individual may request an emergency enrollment in 72 hours for continuity of care. Managed Care to take this back.
7 | 2016-03-21 | Send a list of statues that are listed on the drop down menu | Covered CA | In Progress
8 | 2016-03-21 | Dynamic application immigration questions | MCED | In Progress | An update to the dynamic application questions is targeted for the 2nd quarter of 2017 on the 24 month roadmap.
9 | 2016-03-21 | Can an individual without an SSN get APTC? | Covered CA | In Progress | Advocates have concern with and would like to keep it on the action items to review again.
10 | 2016-04-01 | If plan selection information is not going out until after the transition from restricted scope, how will families be made aware of continuity of care and expedited plan enrollment procedures. Information needs to be provided on how to enroll, who to contact etc. | MCOD | Open | Draft language shared with advocates. Feedback was received and shared back with advocates. There is a placeholder in an upcoming CR to make text edits.
11 | 2016-04-18 | SB 75 beneficiary letter #1 - can we get a breakdown of how many were sent out by county? | MCED | Open | DHCS will share this data at the May 2nd immigration workgroup meeting.
12 | 2016-04-18 | Can the notices for the Affordability and Benefit Program for NQI's be posted on the webpage? | MCED | Open | We are awaiting approval to post them on-line.
13 | 2016-04-18 | Send a copy of the changes to the inconsistency notices | Covered CA | Open

## Completed Action Items
Item Number | Date Logged | Action Item | Owner | Status | Notes
1 | 2015-06-01 | Provide a copy of immigration notices from Covered CA. (Sent out by Crystal 06/01/15) | MCED | Completed 06/01/15. | Notices forwarded to advocates by Crystal on 06/01/15.
2 | 2015-06-01 | PRUCOL - Provide current immigration screenshots for review | MCED | Completed 06/01/15 | Current immigration screenshots forwarded to advocates on 06/10/15
3 | 2015-06-15 | 1. Are questions regarding qualified immigrant, residence since August 1996, veteran or active-duty military used correctly on the application? 2. Advocates would like to know if these questions will only be asked if the applicant is Medi-Cal eligible. For example, would these questions only be asked of applicants who screen financially eligible for Medi-Cal? | MCED | Completed. Closed out on 07/27/15 | 1. CR 32277 (Eligibility Based on LP/QNC (Qualified Non-Citizen)) will deploy functionality to use the 5-year bar information from the application as well as HUB electronic verification information related to whether or not the 5-year applies (yes/no) and has been met (yes/no). 2. There is no current ability to use dynamic functionality to screen applicants for income eligibility to either Medi-Cal or APTC/CSR within the application itself. At this time, the online applicant must answer all required questions, sign the application and click “submit” before eligibility for Medi-Cal or APTC/CSR is determined. As the 5-year bar questions are required for certain applicants based on their response to citizenship/immigration questions, these applicants will need to answer the question before the program they are eligible for is known.
4 | 2015-06-15 | What is the basis for the list for passport county of issuance list? | MCED | Completed. Closed out on 07/13/15 | List for passport county of issuance is created by the Federal Hub. If there are any specific countries that are not listed, advocates will let us know. We believe all the countries are listed accurately.
5 | 2015-06-15 | Provide federal cite | Gabrielle | Completed. Closed out on 07/13/15 | Provided cite 45 CFR 155.305(f)(ii)(B)(2) - regulation that says people with incomes under 100% FPL who are lawfully present but ineligible for Medicaid because of their immigration status can get APTCs and CSRs
6 | 2015-06-15 | Will non applicants be able to skip the SSN question. Will it be clearly stated that providing an SSN is voluntary. Will there be hovered text over the SSN requirements? What will that text be? | MCED | Completed. Closed out on 07/13/15 | The application states that providing an SSN is only required for applicants, however if a non-applicant provides an SSN it will help us review the application faster. Non-applicants are allowed to leave the SSN field blank and continue on with the application. See wireframe for information regarding who must provide an SSN and the exemptions for providing an SSN.
7 | 2015-06-29 | Are the SSN questions and questions regarding qualified immigrant, residence since August 1996, veteran or active-duty military a part of the application CR (6933)? | MCED | Completed. Closed out on 07/13/15 | No, functionality for these questions will be addressed in CR 32277.
8 | 2015-06-29 | What does the appeals process look like? | Covered CA | Completed. Closed out on 08/10/15 | The appeals process is not different for immigration issues. It is described at http://www.coveredca.com/youre-in/file-an-appeal-or-complaint/
9 | 2015-06-29 | How many cases are there for DACA individuals who have had to appeal? | Covered CA | Completed. Closed out on 08/10/15 | None to date.
10 | 2015-06-29 | What threshold languages will the notices be sent in? | Covered CA | Completed. Closed out on 08/10/15 | Notices will be available in English, Spanish, Chinese (traditional), Vietnamese and Korean. The information on the babel page will be translated in the remaining 11 threshold languages.
11 | 2015-06-29 | Will outreach include calls and emails this year? | Covered CA | Completed. Closed out on 08/10/15 | Yes, Covered CA will organize an outbound call unit to resolve inconsistencies. In addition, an e-mail campaign will also be launched.
12 | 2015-06-01 | Is a Medi-Cal denial notice required for individuals who are under Medi-Cal income limits, but not eligible for full scope Medi-Cal due to immigration status, to apply for Covered CA? Ex. An individual with Temporary Protected Status who is eligible for Medi-Cal but is not eligible for full-scope Medi-Cal due to immigration status, but is lawfully present for coverage through the exchange. | Covered CA | Completed. Closed out on 08/24/15 | No. These cases are escalated and require a manual verification and workaround. Service center representatives can handle these.
13 | 2015-07-27 | Provide language for SSN. | Gabrielle | Completed. Closed out on 08/24/15 | Gabrielle provided comment proposed language which is under review.
14 | 2015-06-15 | Covered CA informing notices | Covered CA | Conpleted. Closed out on 08/24/15 | Revisions made, will send out a copy of the revised notices. Notices will be in the most common threshold languages, but will include the babel page which includes all threshold languages. Will release after their review. Notices have been revised and in process of being sent to advocates for comment. Advocates want confirmation that the “Call to Action” is put in the babel sheet and want to review revisions for further comments. Covered CA notified advocates that notices went out so they are unable to make any other changes. Contractors have a different timeline. Next time they will request feedback sooner and get a better understanding of deadlines.
15 | 2015-08-10 | How do we reconcile the APTC amounts for DACA individuals wrongly enrolled in a QHP? | Covered CA | Completed. Closed out on 08/24/15 | Do not have specific appeal for DACA.
16 | 2015-06-15 | Inconsistency numbers related to immigration or citizenship status for this year | Covered CA | Completed. Closed out on 08/24/15 | There are 80,000 inconsistencies related to citizenship/immigration
17 | 2015-07-13 | Send out a copy of the notices that will be mailed to advocates for inconsistencies and pre-term notices. Confirm if the babel line was changed as requested by advocates? | Covered CA | Completed. Closed out on 08/24/15 | The notices have been mailed out. Contractors have a different timeline. Covered CA will request feedback sooner and get a better understanding of deadlines.
18 | 2015-06-15 | What is Individual Taxpayer Identification Number (ITIN) used for? | Covered CA | Completed. Closed out on 09/21/15 | The ITIN number is optional. It can be used if an applicant can not provide an SSN. This number is used by the tax board to verify income. Issue under review--update to follow
19 | 2015-06-24 | Can the ITIN be used for income? What evidence is there that this number can be used for income? Gabrielle will brainstorm for type of evidence. | Gabrielle | Completed. Closed out on 09/21/15
20 | 2015-08-24 | Is there a regulation for restricted scope Medi-Cal? | MCED | Completed. Closed out on 09/21/15 | 22 CCR § 50302
21 | 2015-08-10 | Confirm which forum will be used for NQI wrap related notices that will be implemented. Should it be the AB 1296 notices subgroup, a CC workgroup, or the immigration workgroup? | MCED | Completed. Closed out on 10/05/15 | NQI wrap related notices will be shared in this workgroup.
22 | 2015-08-24 | Send numbers of undocumented children in health plans such as Kaiser etc. | Mark | Completed. Closed out on 10/05/15 | Mark sent numbers. MCED will share with the group.
23 | 2015-07-13 | Health Care for All Children Work Plan | MCED | Completed. Closed out on 10/19/15 | MCED shared all SB 75 documents with advocates.
24 | 2015-08-24 | Will the advocates get a chance to review the Navigator Training modules again? Covered CA will check on draft release date. | Covered CA | Completed. Closed out on 10/19/15 | Covered California is currently developing an "Immigration Advanced Course" to supplement existing training curriculum. Course will be offered to Navigators and other service channels to help answer specific questions related to immigration. Covered California will update on release date and solicit additional feedback from advocates.
25 | 2015-08-24 | Provide update on status of notice changes/process for input to provide adequate review timeline for comments/feedback. | Covered CA | Completed. Closed out on 10/19/15 | The advocates to review new notices including the babble lines before they are released and to provide advocate feedback. This is added as a standing item on the agenda for Covered CA
26 | 2015-06-01 | How is the exchange handling individuals who are not eligible for exchange coverage but apply and get coverage? For example a DACA individual. Will these individuals have to repay/payback subsides? Response provided by Covered CA, however advocates would like a different resolution than the current reconciliation process. | Covered CA | Completed. Closed out on 11/16/15 | These cases would fall under the reconciliation process. They would have to repay subsides. They have the right to appeal. Covered CA to outline its procedures and action it will take to implement. Covered CA has system challenge and is currently going through their internal review process and will share when approved. Covered CA is requesting any cases of DACA individuals in appeals to be forwarded to them and they will review these cases on a case by case basis.
27 | 2015-11-02 | Provide what aid code E1 is | MCED | Completed. Closed out on 11/16/15 | E1 # Medi-Cal/HF Bridge - There is no one in this aid code; it has been updated as a pre-ACA on the aid code chart.
28 | 2015-11-02 | Provide the script that accompanies the CEC training slides | Covered CA | Completed. Closed out on 11/16/15 | Script sent by email on 11/3/15
29 | 2015-07-27 | Dynamic functionality - where can we track this item? | MCED | Completed. Closed out on 11/30/15 | If the dynamic functionality is related to immigration then will use this group.
30 | 2015-11-16 | Will SB 75 FAQs be translated? | MCED | Completed. Closed out on 11/30/15 | No SB 75 FAQs will not be translated. They will be posted in English on the SB 75 website.
31 | 2015-06-01 | Provide a list of acceptable Remote Identity Proofing (RIDP) identity documents. | Covered CA | Completed. Closed out on 12/14/15 | Advocates would like the list to be at least as inclusive as the federal list. List updated to reflect federal list. Revised list sent out on 11/30/15. The list has been expanded on page 2.
32 | 2015-10-02 | Individuals taking CEC training are being advised that an applicant/beneficiary must have an SSN to apply through CalHEERS, even individuals in immigration categories such as student visa holders who would not necessarily have an SSN. Is this correct? If so, how can these eligible people apply? If not, can some sort of message to CECs be issued clarifying this? | Covered CA | Completed. Closed out on 12/14/15 | Covered CA provided advocates the script that accompanies the CEC training slides. Advocates provided feedback. Covered CA is editing the script for 2016. However the best way to get information out is through webinar training. Covered CA will inform advocates when the next webinar is to get correct messaging out. Next webinar date is a new action item and this item is being closed out.
33 | 2015-07-27 | What is the new screening process for failure to file income taxes | Covered CA | Completed. Closed out on 12/28/15 | Consolidating this item with number 7 "Individuals with an ITIN are considered as non tax filers. How many non tax filers are there? "
34 | 2015-11-30 | When is the next webinar for CEC so advocates can provide messaging? | Covered CA | Completed. Closed out on 12/28/15 | Next webinar is in January. Covered CA is requesting any slides/wording recommendations by the end of the week 12/18/15.
35 | 2015-11-16 | Can we add information on public charge? | MCED | Completed. Closed out on 12/28/15 | MCED can not provide advice on public charge. MCED added the link from the USCIS website regarding public charge to the SB 75 FAQs as requested.
36 | 2015-11-16 | What is the next step for FAQs? | MCED | Completed. Closed out on 12/28/15 | Final FAQs shared with the workgroup. Only fatal flaws will be accepted into the document so we can post the questions.
37 | 2015-12-14 | When will the Provider Webinar be held for SB 75? | MCED | Completed. Closed out on 12/28/15 | The provider engagement meeting will be on January 21, 2016.
38 | 2015-12-14 | What is the link to the drop box to that counties do not have to create the same material. | MCED | Completed. Closed out on 12/28/15 | https://www.dropbox.com/sh/x57ms7tyguravwu/AACEU3W1XTZeH_Tmh_bl_tnNa?dl=0
39 | 2015-12-24 | Children who age out of full scope benefits at 19 years old, are they protected by CEC until Redetermination? Are they protected by soft pause or any other Consumer Protection Program? If they change immediately from full scope to restricted when they turn 19 is it the month before their 19th birthday or the last day of the month of their 19th birthday? | MCED | Completed. Closed out on 12/28/15 | Age 19 is not a protection from CEC. Age is a change of circumstance. An individual that is 18 for one day of the month is considered 18 for the month and will remain in full scope Medi-Cal until the following month. If an individual turns 19 the first day of the month, he/she is considered 19 for the whole month and will not be eligible.
40 | 2016-01-07 | Has the provision on Minor Consent changed at all in relation to the SB75 expanded MC for undocumented clients? Are undocumented clients now eligible for Minor Consent services? | MCED | Completed. Closed out on 01/11/16 | SB 75 does not change minor consent rules.
41 | 2016-01-11 | What MEDIL provides work arounds? | MCED | Completed. Closed out on 01/25/16 | http://www.dhcs.ca.gov/services/medi-cal/eligibility/Documents/MEDIL2014/MEDILI14-08.pdf
42 | 2015-11-16 | Is Covered CA using the new formula to determine APTC for families with non lawfully present immigrants. | Covered CA | Completed. Closed out on 01/25/16 | Covered CA confirmed that they are using the new formula to determine APTC for families with non lawfully present immigrants. This is a part of change request (CR) 36110. Covered CA sent out a screenshot of the CR to the group.
43 | 2015-12-14 | Continuity of Care for children who are in health plans and will be enrolled in full scope Medi-Cal | MCED/ Managed Care | Completed. Closed out on 01/25/16 | Current continuity of care applies. Beneficiaries will be able to continue to request a provider to join. Beneficiaries will also be able to complete a Medical Exemption request.
44 | 2015-11-02 | What is the new screening process for failure to file income taxes? Individuals with an ITIN are considered as non tax filers. How many non tax filers are there? | Covered CA | Completed. Closed out on 02/08/16 | Received non tax filer files for 2014 from IRS for individuals who have not filed by received APTC. Getting clarification from IRS regarding how ITIN filers fit into this file. Data for ITIN filers came back as non filers.
45 | 2015-12-14 | Will SAWS 2 Plus need any edits/revisions for SB 75? | MCED | Completed. Closed out on 02/08/16 | MCED reviewed the SAWS 2 Plus form and confirmed that there are no edits/revisions needed.
46 | 2016-01-11 | Can plan selection packets be sent out earlier? | Managed Care | Completed. Closed out on 02/08/16 | No. Plan selection packets can only be sent when the person is in a full scope aid code.
47 | 2016-02-08 | Send scenarios for NQIs | Jen Flory | Completed. Closed out on 02/22/16 | Scenario's sent by Jen.
48 | 2016-02-08 | Is there a change request in 16.2 that allows for non applicants to skip SSN questions? | MCED | Completed. Closed out on 02/22/16 | CR 11708, expected to be implemented in 16.2, will suppress certain questions related to non-MAGI screening criteria and citizenship/immigration status for non-applicants. The SSN question will not be suppressed for non-applicants as a result of this CR. Separate from this CR, DHCS is working with CalHEERS to ensure the SSN question is functioning appropriately, as non-applicants are not required to provide their SSN.
49 | 2016-02-08 | For the SB 75 aid code crosswalk, if the SB 75 children are being transitioned into the full-scope aid code, how is DHCS handling the designation of state funding versus | MCED | Completed. Closed out on 02/22/16 | DHCS will handle the funding on the back end which is current policy for individuals who are state funded but in a full scope Medi-Cal aid code.
50 | 2016-02-08 | Share new RIDP process/screenshots to be released March 2016. | Covered CA | Completed. Closed out on 02/22/16 | Sent out by Covered CA.
51 | 2016-01-25 | SB 75 Implementation recommendations from advocates | MCED | Completed. Closed out on 03/07/16 | DHCS has verbally responded to SB 75 Implementation recommendations.
52 | 2016-02-08 | When will SEP start for NQIs? | MCED | Completed. Closed out on 03/07/16 | Enrollment for NQI's will begin during open enrollment. There will not be a new SEP created for the wrap.
53 | 2016-02-08 | Are the SAWS ready for a May implementation if there is system readiness | MCED | Completed. Closed out on 03/07/16 | DHCS is working closely with the SAWS to ensure system readiness.
54 | 2016-02-08 | What is the formal policy or regulation that does not allow plan selection packets to be sent out earlier? | MCOD | Completed. Closed out on 03/07/16 | 42 CFR 438.10 governs what MCOD sends out. MCOD can not provide a choice that is not available.
55 | 2016-01-25 | Can the workgroup see the current template notice for terminations from Covered CA? | Covered CA | Completed. Closed out on 03/21/16 | Notices sent to the group.
56 | 2016-03-07 | Can enrollment packets be sent out in beneficaries language? | MCOD | Completed. Closed out on 03/21/16 | Yes, packets will be sent in threshold languages.
57 | 2016-02-08 | Can we get a report back on the Provider Engagement meeting on 01/21. What are the other plans for provider engagement? | MCED | Completed. Closed out on 04/04/16 | Provided verbal report on Provider Engagement meeting.
58 | 2016-04-01 | When prior to may 16 will the department be able to certify may 16 as the date certain for implementation | MCED | Completed. Closed out on 04/04/16 | Implementation is currently set for 05/16/16. DHCS will not know a definitive date until testing is completed.
59 | 2016-04-04 | Provide link to NQI webpage | MCED | Closed | http://www.dhcs.ca.gov/services/medi-cal/Pages/Affordability-and-Benefit-Program.aspx
60 | 2016-04-04 | How can we find out upfront if someone has ESI so they are not eligible for the wrap? | Covered CA | Closed | Information about ESI is attested to on the application.